## Task_Table
2013-07-16
Task Id | Active | Task Mode | Name | Start | Finish | Status | Dependency | Comments and milestones | Point Person
A |  |  | Dashboard Scope and Planning
| No | Auto Scheduled | Set program scope, budget, and resources | [5 empty] | ?
1 | No | Manually Scheduled | Create oversight group with members and roles |  |  | not started |  | CCP data committee began looking at it, governance not clear
2 | No | Manually Scheduled | Define Dashboard Objectives and scope |  |  | not started
3 | No |  | Project Budget and ongoing resources |  |  | not started |  | County owns excel based dashboard software, human resources not allocated
4 | No | Manually Scheduled | Decide on Strategic outputs and outcomes |  |  | not started |  | Outcome measures begun in June, master list not completed
B |  |  | Design Requirements
| No | Auto Scheduled | Definition creation and finalization
5 | No | Manually Scheduled | Interviews with stakeholders on dashboard features and measures |  |  | not started
6 | No | Manually Scheduled | Document expectations and requirements as to exploratory vs. reporting for future development |  |  | not started
7 | No | Manually Scheduled | Develop storyboard based on design requirements |  |  | not started
8 | No | Manually Scheduled | Build prototype dashboard and dataset |  |  | not started
C |  |  | Build and Implement
| No | Auto Scheduled | Design Process
9 |  |  | Design user interface |  |  | not started
10 |  |  | Complete user testing to determine reporting and data needs of key stakeholders |  |  | not started
11 |  |  | Confirm data sources and plan update cycle |  |  | not started
12 |  |  | Develop drill down logic and interactions |  |  | not started
| No | Auto Scheduled | Data Collection and Warehouse Development
13 |  |  | Design and specify data warehouse for compiliation of county data |  |  | not started
14 |  |  | Develop queries and data dictionary |  |  | not started
15 |  |  | Develop quality control cycle for data publishing |  |  | not started
| No | Auto Scheduled | Initial Deployment
16 |  |  | Demonstrate protoype to data workgroup and key stakeholders |  |  | not started
17 |  |  | Confirm access and usability for all web based users |  |  | not started
18 |  |  | Create ongoing upgrade and roadmap for future data elements |  |  | not started
19 |  |  | Create CCP/internal county view vs public view |  |  | not started
D |  |  | Maintenance
| No |  | Continuity and upkeep
20 |  |  | Integrate dashboards and public facing reports into website |  |  | not started
21 |  |  | Create permanent oversight committee for outcome measures and reporting |  |  | not started
22 |  |  | Transition management to non-technical project person |  |  | not started
23 |  |  | Document project handoff and data sources |  |  | not started

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work type | Units | Amount